# Study plan for exploring Position Trainable Transformers for Computer Vision

## Month 1-2: Foundations of Transformers and Computer Vision
- Week 2-5: Transformers Overview
  - Readings:
- "Attention Is All You Need" by Vaswani et al. (2017). (READ, READ, READ)
- A primer on self-attention mechanisms.
  - Videos/Courses:
Such as — Stanford's CS231n lectures on transformers (lecture 9)
  - Milestone 1:
    - Experiment with simple transformer architectures using PyTorch or TensorFlow (Preferably PyTorch).
- Week 0-5: Computer Vision with Deep Learning
  - Readings:
Goodfellow et al.'s “Deep Learning” (focus on CNNs and vision-specific chapters).
  - Milestone 2:
Implement basic CNN architectures like ResNet and VGG for image classification tasks on simple available datasets like CIFAR-10.
  - Project:
Use a pre-trained vision transformer (ViT) on a simple dataset (ImageNet or CIFAR-10) and evaluate its performance.
## Month 1-2: Vision Transformers (ViTs)
- Week 3-6: ViT Basics
  - Readings:
"An Image is Worth 16x16 Words: Transformers for Image Recognition at Scale" by Dosovitskiy et al. (2020).
  - Videos/Courses:
Hugging Face Course on Vision Transformers.
  - Milestone 3:
Train a ViT from scratch on a small custom dataset (e.g., MNIST, CIFAR-10 or Neadvance may provide a dataset until then).
- Week 3-6: Advanced ViT
  - Readings:
- "Scaling Vision Transformers" by Zhai et al. (2021).
- "Exploring Simple Siamese Representation Learning" (related to self-supervision).
  - Milestone 4:
Fine-tune a pre-trained ViT model on more complex datasets, such as ImageNet.
## Month 3-: Exploring Position Trainable Transformers
- Week y4-y5: Positional Embeddings
  - Readings:
- Study how positional encodings work in transformers.
- Papers like "Understanding Positional Encodings in Transformers" (from different research).
  - Milestone 5:
Experiment with modifying the positional embeddings of a ViT model (train with different configurations).
- Week y5-y6: Position Trainable Transformers (PTT)
  - Readings:
Papers related to Position Trainable Transformers or Dynamic Positional Encodings.
  - Milestone 6:
Implement position trainable modules and apply them to standard transformer architectures.
  - Project:
Compare the results of static vs. position trainable transformers on a custom dataset.
## Month x2-x3: Applications of Transformers in Computer Vision
- Week y6-y7: Transformer Applications
  - Readings:
- "End-to-End Object Detection with Transformers" (DETR).
- "Swin Transformer: Hierarchical Vision Transformer using Shifted Windows".
  - Milestone7:
Implement DETR and Swin Transformer models for object detection tasks.
- Week y7-y8: Multimodal Transformers
  - Readings:
"Image-Text Pre-training for Vision and Language" (CLIP, ALIGN).
  - Milestone 8:
Use CLIP models for image-text understanding tasks and fine-tune it for specific use cases.
## Month x2-x3: Self-Supervised Learning and Transformers (In case you are interested)
- Week y8-y9: Self-Supervised Learning Basics
  - Readings:
Papers on self-supervised learning such as "SimCLR" and "BYOL".
  - Milestone 9:
Implement a self-supervised learning framework using vision transformers.
## Month x3-x4: Experimentation and Final Project
- Week y9-y10: Research and Experimentation
- Start developing a final research project on Position Trainable Transformers in a specific domain (e.g., object detection, segmentation, hyperspectral imaging).
- Formulate a hypothesis, plan experiments, and define evaluation metrics.
- Week y11-y12: Writing and Reporting
  - Prepare a detailed report on your findings, comparing performance of position trainable transformers with conventional transformers across various tasks.
Write a research paper based on your project with experimental results (—optional—).
By the end of this study plan, you should have a deep understanding of Position Trainable Transformers in the context of computer vision, be able to implement various transformer architectures, and contribute to research in this field.
ALSO, KEEP IN YOUR MIND REGARDING NEADVANCE’ REGULARIZATIONS WE EXPECT A COMPLETE COMPREHENSIVE REPORT (E.G. POWERPOINT OR A WORD FILE) AFTER EACH MILESTONE.